## Slide 1
PRESENTATION TITLE and subtitle
……………………………. Speaker name, Partner
WP 4
Implementation
……………………………. Mihai Ștefan, Cornelia Predoi, EICD

## Slide 2
To prepare open access e-learning modules
To enable university and company partners to learn how to develop e-learning material
To test the effectiveness of blended course
To deliver both theoretical and practical course as e-learning product, in which
  Course is recorded
    Practical module is performed with students but it is recorded, then appended to the e-learning theoretical module
WP 4 - aims

## Slide 3
T4.1 Activation of the internal procedures for the ECTS recognition (EICD Leader; University partners)
T4.2 Setup the technical environment for the e-learning system (EICD Leader, all)
T4.3 Developing the Action Plan for the e-learning course (EICD Leader; all Uni.).
T4.4 Turning the training materials into e-learning modules (EICD Leader; All)
T 4.5: Testing the e-learning modules through a pilot phase (led by EICD; all)
T 4.6: Turning feedback into improvements of the e-learning course (led by EICD; all).
Tasks

## Slide 4
T 4.2 Setup the technical environment for the e-learning system – deadline Jan 2023

## Slide 6
T 4.2 Setup the technical environment for the e-learning system – deadline Jan 2023
Theoretical block
Connection to T4.4
Each university partner will develop one e-learning sub-module of at least 2 hours for the theoretical module.
The implementation will consist in recording the e-learning with respecting the guidelines provided by R4.2 and R4.3.

## Slide 7
T 4.2 Setup the technical environment for the e-learning system – deadline Jan 2023
Theoretical block
Proposition
6 videos – 20 mins each, per University partner
A total of 30 videos (30 ppt presentations)
Pre- and post-test questionnaire?
Trying to link clinical scenarios to one 20 min presentation
Video recordings – voice over slide PPT?

## Slide 8
T 4.2 Setup the technical environment for the e-learning system – deadline Jan 2023
Clinical scenario = practical simulation
Connection to both T 4.4 and T 5.3
Each university partner will develop 5 e-learning practical simulations through taking frontal classes. Trainers will get the signature of the “consent form” from each student attending the course.
The classes will follow the approved scripts. The whole (performance with simulation device and subsequent debriefing) practical simulations will be recorded so that this second e-learning module will consist of a movie featuring the enacted scripts by students.

## Slide 9
T 4.2 Setup the technical environment for the e-learning system – deadline Jan 2023
Clinical scenario = practical simulation
The classes will be attended by at least 40 LEARNERS – as specified in target groups, the category of LEARNERS includes Medical students, residents, healthcare professionals, physicians who need (want) to learn and revive emergency medical skills - (at least 200 LEARNERS in total across University partners).

## Slide 10
T 4.2 Setup the technical environment for the e-learning system – deadline Jan 2023
Clinical scenario = practical simulation

## Slide 11
T 4.2 Setup the technical environment for the e-learning system – deadline Jan 2023
Can we use google classroom?
The project stipulates we need a youtube channel to upload all video materials
Also, it should be readily available to all those interested
Should we use a dedicated section in website?
How do we give pre- and post-course tests?

## Slide 12
T 4.3 Developing the Action Plan for the e-learning course – deadline Feb 2023
We will develop:
A consent form for students
Methodologies and procedures to deliver e-learning course
Procedures to evaluate e-learning course
Procedure to incorporate recommended improvements
We need partners:
To assign a responsible person from each university partner

## Slide 13
T 4.4 Turning the training materials into e-learning modules – Feb-Jun 2023
Outputs:
Theoretical modules
Practical simulations
Skill training videos? – can company partners help?
Interim and final tests to verify learning outcomes
Specific questionnaire for evaluating learning course in terms of content and teaching methods
Other materials:
PPt slides
Course texts
Infographics

## Slide 14
T 4.5 Testing the e-learning modules through a pilot phase – Jun-Jul 2023
The university partners will get tested by at least 40 LEARNERS from non HEIs partners (contacted by HEI partners), and at least 3 companies from no-partner Companies.
We propose that EICD and SRATI (associated partner) test the modules
We can have a workshop at the national congress (may 2023)
Companies to find no-partner companies

## Slide 15
T 4.6 Turning feedback into improvements of the e-learning course – Aug-Sept 2023
Feedback will be analysed to develop corrective measures for the e- learning course.
The improvements will flow into the e-learning modules in order to deliver the final version of the course.

## Slide 16
University partners have committed to introduce Emergency scientific and educational outputs (courses designed in WP3) as university Courses in established curricula.
Therefore, the partners will take all the steps to define the number of ECTS for the courses designed in WP3, according their common internal rules.
The courses will be integrated in the annual curricula, even if in a pilot version, and they will be the only courses on the subject available for the academic year.
T 4.1 Activation of the internal procedures for the ECTS recognition – deadline Jan 2023

## Slide 17
Problems
Not all academic partners are Universities
Can Universities insert SAFETY in curriculum as sole course?
Not all countries follow ECTS system
Potential solution – EACCME accreditation of on-line course for those partners unable to obtain ECTS credits
T 4.1 Activation of the internal procedures for the ECTS recognition – deadline Jan 2023

## Slide 18
Thank you!