## Slide 1
2nd Official Project meeting
WP6 updates
……………………………. Fedele Colantuono, UniFg
The European Commission's support for the production of this publication does not constitute an endorsement of the contents, which reflect the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.

## Slide 2
The aims of this WP are:
• to guarantee the efficient management of the project,
• the overall control of all activities,
• the organisation of partners Meeting,
• the regular flow of information,
• to ensure results are attained on target delivery dates,
• the administrative and financial support to all the partners,
• to liaise with EACEA
Partner logo
Fedele Colantuono, 5 May 2021 Page 1
WP6 - Project Management
(leader: UniFg with the technical support of ValueDo,
all partners involved)

## Slide 3
- T 6.1: Overall Management and preparation of timesheets (UNIFG Leader; Valuedo; all partners)
Quarterly report : I (completed);
II (by 10th May)
- T 6.2: Preparation of and participation in Project Meetings (ValueDo Leader; all partners)
PM1 - Kick Off Meeting (M1), - 25, 26 Nov. & 14-16 Dec. 2020
Meeting WP2, 22-01-2021
Meeting WP1, 03-02-2021
Meeting WP1,WP2, WP9, 17-03-2021
PM2 - month 6, 05-05-2021
other bilateral and partners meetings dedicated to specific subjects
Partner logo
Fedele Colantuono, 5 May 2021 Page 2
Tasks implementation

## Slide 4
R6.1 Partner Agreement
Legal documents, budget transfers
R6.2 Management Tools
- template for time sheets;
- financial and administrative guidelines;
- GANTT and task distribution
- File with all the deadline
R6.3 Project Meetings documents
agendas
participant lists
minutes
R6.4 Interim report (M18)
Partner logo
Fedele Colantuono, 5 May 2021 Page 3
WP6 results

## Slide 5
Request of change partner and inclusion of an associated partner
The partner Hospital Clinic de Barcelona is replaced by Fundació Clínic per a la Recerca Biomèdica but remains as affiliate in the project.
Request was sent officially to the EACEA on 17/02/2021 and approved on 16/03/2021
Partner logo
Fedele Colantuono, 5 May 2021 Page 4
1st Project amendment

## Slide 6: Thank you!