## Slide 1: PLANET4 Simulation Approach For Education and Training in emergencY
WP8 description
Project Evaluation
The European Commission support for the production of this publication does not constitute endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein

## Slide 2: WP8 in a nutshell
WP8, lead by EICD in collaboration with ValueDo, aims to evaluate and guarantee the project quality
The Evaluation Process will rely on the Quality Assurance Plan (QAP), as defined in WP7 – lead by ValueDo
WP8 will determine whether the project planning and implementation are effective and if the planned results / expected impacts are met
The evaluation will be conducted in parallel to the rest of the WPs, as defined in each one of them
EICD will ensure the overall monitoring of activities and indicate the adjustments needed to meet to project’s quality standards

## Slide 3: Evaluation Process
How will the Continuous Improvement Process (CIP) work?
The evaluation process focuses on the outcomes and impacts of the project’s activities
The evaluation’s aim is to systematically collect, analyze and use data to answer questions about the effectiveness of the project
The activities will be carried out using internal and external resources
The evaluation, via Continuous Improvement Process (CIP), will guide the project management and partners on how to improve the implementation of the project

## Slide 4: Continuous Improvement Process (CIP)
Operation
Do
Support
Performance Evaluation
Planning
Check

## Slide 5: Continuous Improvement Process (CIP)
Operation
Quality Assurance Plan (QAP) (WP7)
Organizational risks
Assess quality parameters provided by QAP
Do
Support
Performance Evaluation
Planning
Plan
Act
Check

## Slide 6: Continuous Improvement Process (CIP)
Operation
Quality Assurance Plan (QAP) (WP7)
Organizational risks
Assess quality parameters provided by QAP
Perform internal and external evaluation
Evaluation processes meet the required quality parameters
Control of processes to meet the quality requirements set by QAP
Evaluate overall activities and proactive control and report
Do
Support
Performance Evaluation
Planning
Plan
Act
Check

## Slide 7: Continuous Improvement Process (CIP)
Operation
Quality Assurance Plan (QAP) (WP7)
Organizational risks
Assess quality parameters provided by QAP
Perform internal and external evaluation
Evaluation processes meet the required quality parameters
Control of processes to meet the quality requirements set by QAP
Evaluate overall activities and proactive control and report
Do
Monitor, analyze, evaluate QAP
Internal and external evaluation
Evaluation and determination of required improvements
Support
Performance Evaluation
Planning
Plan
Act
Check

## Slide 8: Continuous Improvement Process (CIP)
Operation
Quality Assurance Plan (QAP) (WP7)
Organizational risks
Assess quality parameters provided by QAP
Perform internal and external evaluation
Evaluation processes meet the required quality parameters
Control of processes to meet the quality requirements set by QAP
Evaluate overall activities and proactive control and report
Do
Cooperation with WP7 leader to manage quality control standards
Manage and cooperate with all partners and actors involved in the evaluation process (WP8)
Monitor, analyze, evaluate QAP
Internal and external evaluation
Evaluation and determination of required improvements
Support
Performance Evaluation
Planning
Plan
Act
Check

## Slide 9: Evaluation Process framework
The framework of the Evaluation process includes:
Description of roles and responsibilities within the partnership
Provision of Key Performance Indicators (KPIs)
Description of the evaluation tools and procedures to be adopted with respect to categories of outputs
Overview of the Evaluation Process itself

## Slide 10: Objectives of the Evaluation Process
The evaluation provides information to help improve the project’s progress in two ways:
  Information on whether the aims and objectives are being met
  Information on whether the project outcomes fit the expectations regarding knowledge, innovation and practical application
  The evaluation aims at ensuring satisfaction of interested parties and demonstrate impacts in the field
  In addition, the evaluation may also provide new insights that were earlier not anticipated

## Slide 11: Milestones & Results
Some of the project’s milestones (ML) will be object of a specific evaluation made by each project partner and external and independent subjects (at least 2 per each ML). In particular:
ML1
ML2
ML6
Every evaluation of Results and MLs will be taken into consideration in order to improve or reshape the considered outputs, if necessary

## Slide 12: Link of WP8 with the other WPs
WP7 has a strong connection with WP8, that establishes the evaluation's main principles through the QAP
Each partner will fill in a Quarterly Report describing the activities conducted in every WP. The reports will be checked by the LPs of WP7 (ValueDo) and WP8 (EICD) against the project indicators and deadlines
The Evaluation Process will begin with the project implementation and will continue during its progress, thus being linked with all WPs in general

## Slide 13: Tasks in WP8
T 8.1: Elaboration of evaluation tools for partners and external experts (EICD Leader; ValueDo Fellow)
T 8.2: Internal evaluation by partners (ValueDo Leader; All)
T 8.3: External independent evaluation (EICD Leader; All)

## Slide 14: Task 8.1
The task is led by EICD, with the support of ValueDo
EICD will draft evaluation questionnaires to collect feedback from partners (to be included in Quarterly Reports - in collaboration with WP7 Leader) on all the MLs, referring to QAP and indicators already defined in WP7
The partners will evaluate all MLs and Results through the questionnaires (to be included in Quarterly Reports)
External evaluators (at least 2) will be asked to assess ML1, ML2, ML6. EICD will prepare interviews for collecting feedback from the external experts
The criteria for the selection of the experts will be proposed by EICD and agreed by the partners

## Slide 15: Task 8.2
The task is led by ValueDo with the support of the entire partnership
This task refers to the internal evaluation processes, to be implemented by partners
All MLs will be evaluated through Quarterly Reports, which will include the questionnaires mentioned in T8.1
ValueDo will collect the filled-in questionnaires together with the Quarterly Reports and will elaborate the Overall Evaluation Report (OER)
For the elaboration of the OER, ValueDo will consider the feedback collected in T8.1 and also information from T8.3

## Slide 16: Task 8.3
The task is led by EICD with the support of the entire partnership
This task refers to the external evaluation processes, to be implemented by external and independent experts
EICD, with the support of UNIFG, will select a short list of 6 Independent evaluators, among which 3 will be selected by the Steering Committee, in the composition provided in the QAP (R7.1)
For the milestones mentioned earlier (ML1, ML2 and ML6) EICD will conduct the semi-structured interviews for external experts, as prepared in T8.1
EICD will prepare a specific report with the feedback received by the experts. This report will feed the Overall Evaluation Report (OER)

## Slide 17: In conclusion...
A successful evaluation process will not only ensure project quality, but can also provide new information and aspects not foreseen earlier
The Quality Assurance Plan (QAP) plays a key role in achieving optimal results regarding evaluation. For that reason, cooperation between EICD and ValueDo is vital
WP8 will determine the project’s effectiveness and continuous process of improvement during implementation
EICD, as a coordinator of WP8, needs to be in full cooperation with all the partnership, receiving progress information and feedback
Monitoring of project activities and partners’ feedback will lead to the adaptations needed to meet the quality standards set

## Slide 18: Thank you!
Contact Information:
…………………