3rd Virtual Meeting
17th March 2021

-----------------------------------------------

The European Commission's support for the production of this publication does not constitute an endorsement of the contents, which reflect the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein

Agenda:

- WP1: updates on the pilot research (HUBc)

- WP1: planning T1.3 in-depth literature review on team composition in Emergency (UiS)

- WP2/T2.3: updates on pilot test and official launch of the surveys for students and academics (UniFg)

- WP2/T2.4 Presentation of the Action Plan and questionnaires draft version for entrepreneurs (UniFg)

- WP9: Updates on dissemination activities (InfoTech)

Participants:

- University of Foggia (UNIFG) represented by Fedele Colantuono, Francesco Barberio, Roberta Caporusso and Giacomo Errico;

- University Clinic Hospital of Barcelona (HUBc) represented by Juan Perdomo, Lidia Gomez, Sara Darriba, Cristina Ibanez;

- “Prof. Dr. CC. Iliescu” Emergency Institute for Cardiovascular Diseases (EICD) represented by Daniela Filipescu, Mihai Stefan, Liana Valeanu and Cornelia Florescu;

- Ludwig-Maximilians University of Munich (LMU) represented by Marc Lazarovici;

- University of Stavanger (UIS) represented by Thor Ole Gulsrud, Camilla Normand, Peter Dieckman and Une E. Stømer;

- ValueDo (VALUE) represented by Giuditta Pasta;

- Infotech (INFO) represented by Antonio Scrocco;

- Take the Wind (TWW) represented by Rita Flores, Pedro Pinto and Silvério Sousa Mendes;

- Laerdal (LAE) represented by Novella Callero;

- Alpha Medical Concepts (AMC) represented by Carmen Obergrabner.

WP2/T2.3: updates on the official launch of the surveys for students and academics (UniFg)

Francesco (UniFg) updates the partners on the feedback and suggestions collected during the pilot test of the surveys for academics and students performed by the partners UniFg, HUBc, EICD, LMU. UIS and TWW (full presentation available here).

During this stage, they received 11 feedbacks from Academics and 17 from Students.

Francesco points out that the majority of the students expressed the preference to receive the survey in their native language. However, Francesco stresses out the importance of having also an English version of the survey for dissemination on the SAFETY social medias. He underlines the following points and changes in the questionnaires, also discussed during a previous follow-up meeting with the other national coordinators of this task:

- Translation of the questionnaires in native languages;

- Students’ target group: try to disseminate above all to university students (medicine 5-6th years, nurse and midwifery 3rd year) or ask postgraduate students to think about their emergency education during the university career before their degree;

- Academics/Experts: ask them to refer their answers only to university students or first-year postgraduates;

- The number of the choice sets of part II reduced from 8 to 6 tables.

- Francesco will send to all partners the Italian version of the questionnaires, so they can double check after the translation the sense of each questions or wording is the same. In any case, they all agree to have the English versions as master.

He also reminds that, as discussed during previous project meetings, the targets to reach for the surveys are the following:

- At least 500 students from each country;

- At least 100 academics from each country.

The English version of the survey is available in the official folder of the project on GDrive.

Francesco suggests uploading all the links of the surveys in the alternative languages on the SAFETY website to allow the partners to reach a wider audience. The partners agree to provide both versions (the one in the national language and the English one) and therefore always keep the English version as a reference for the responders. All partners agree.

Antonio (InfoTech) will update the website as soon as the national coordinators of this task will generate the link for the google surveys in the different languages.

Regarding expected numbers for the surveys, some representatives (from EICD and LMU) expressed their concerns about these numbers, since they seem to be high and quite difficult to reach in their environment.

At this point, Fedele highlights that in order to have a robust data set for statistical analysis, also in case of potential publications, it is wise to count on large numbers, but of course these are indicative and they may change among countries. In any case, he suggests that it is important to start with these goals and try to reach them, also enlarging the surveys among networks and other contacts every partner may count on, outside its university. For this reason it will be important to have some intermediate checks and evaluate on time the numbers we will get during the surveys and in case take corrective actions to improve them

Next deadlines and workflow:

- All University partners to start generating the surveys on google enquires and make the links available to spread the surveys for academics and students in the week between 22.03.2021 and 26.03.2021;

- All University partners to collect all data from the surveys by 31.05.2021;

- UniFg to perform an intermediate check for the surveys performance in the beginning of April, although Francesco, as task leader, will be constantly in touch with the different national coordinator of this task.

WP1: updates on the pilot research (HUBc)

Juan (HUBc) shows the updates on the pilot research conducted by HUBC in Catalan Region (full presentation here). The research involved 9 universities, 35 hospitals and 1 Emergency Service.

Juan informs that within two weeks HUBc will provide the Final Report on the research (on 31.03.2021, as scheduled) and access to the Red Cap platform for data collection.

Marc (LMU) expresses some concern about the research, as German universities will have a lower level of information than the one shown by Juan from the Spanish ones. Juan reassures him that at the beginning of his research, he had the same concern, but then he realized that hospitals do not promote as universities usually do their research and so at the end they had a delighted surprise. He also reminds that the research is intended as desk research, so every partner should perform it in this way, since the majority of information about courses are available online. He will also provide details about how to start an online search.

WP1: planning T1.3 in-depth literature review on team composition in Emergency (UiS)

Camilla (UiS) informs the partners that the search process for the articles is finalized with about 1740 scientific papers uploaded on Rayyan (a web application to help systematic review authors perform their job). UiS team is ready to start the initial screening process, excluding and including articles by title and abstract.

To achieve the optimal study protocol, the UiS team wishes that each article is screened by two people and therefore they require screening assistance from the partners.

Camilla shows how Ryyan works starting from the following keywords for the research: “optimal team composition in emergency”. Only articles describing the “optimal team composition in emergency” can be included in the research. The articles to be included refer both to real life and to simulation training.

The inclusion criteria to follow are:

- Trauma

- Cardiac resuscitation

- Paediatric emergencies

- Neurological emergencies

- Surgical emergencies

- Internal medicine emergencies

- Obstetric emergencies

The exclusion criterion is just one: emergencies in already hospitalized patients.

The partners are asked to express their availability and start screening the articles already found by UiS, analysing the abstract of each of them to understand if they can be included or excluded according to the listed criteria. For this aim, Camilla will send an email to the partners asking for their expression of interest to cooperate on this search. After she will get the names of participants, it will be possible to share the articles found among people.

Juan (HUBc) also suggests adding in the inclusion criteria for searching the cardio-pulmunary resuscitation in intensive care units (CPR in ICU), and Camilla agrees to add it and check if there are papers.

Next deadlines and workflow:

- UiS to send the invitation to access Ryyan by 25.03.2021;

- UiS to finalize T1.3 in-depth literature review on team composition in Emergency according to the exclusion/inclusion criteria by 18.05.2021.

WP2/T2.4 Presentation of the Action Plan and questionnaires final version for entrepreneurs (UniFg)

Fedele and Giacomo (UNIFG) start presenting the Action Plan and the questionnaires for entrepreneurs (full presentation here).

Fedele reminds the importance of cooperation between academia and companies in the SAFETY project and the key role of companies partners, especially during the entrepreneurs' needs surveys.

The surveys for companies is developed in two steps.

The first step is represented by a questionnaire dedicated to all companies to be submitted online, and structured in this way:

- Part I – General data from Companies

- Part II – Structured questionnaire based on Likert’s scale composed by 4 groups (5 questions for group)

- Group 1: presence of medical staff within companies

- Group 2: importance of research and communication within the company

- Group 3: presence of companies in university’s program

- Group 4: medical training in simulation

The second step of the survey is represented by a questionnaire with open questions (semi-structured interviews) to be performed in addition for SAFETY companies’ partners and selected external companies. The interview is not compulsory and can be done by sending the questionnaire through emails or contacting the companies by phone or online meetings for a brief discussion.

The questions are the following:

- What are the roles that a medical figure can play within your company? (e.g. researcher, development of new tools and equipment, trainer,  Medical Science Liaison)

- What are the necessary skills that these doctors should obtain during their studies in order to be able to offer the right contribution to your company?

- What is the contribution that companies, through advanced or basic medical simulation, can provide for students' training? (existing or future ideas and projects) Give also examples of your collaboration or partnership with scientific societies or local universities.

- What can be the University’s contribution, through their study courses, in developing or using simulation tools for students’ training? (educational workshops, biomedical science courses, internships in companies)

All partners will perform the investigation through the contacts they have indicated in the shared companies list. Fedele invites all the company partners to spread the questionnaire hopefully also through other different networks they have. All company partners will do their best to reach the expected target.

Next deadlines and workflow:

- All partners to send feedback to UniFg on the questionnaire for the companies  and the names of the task responsible (national coordinator) by 25.03.021;

- by the end of March it will be performed a pilot test with the companies partners in order to have a definitive version of the questionnaires soon and start the survey by 5th April till end of May, with an intermediate check at the end of April.

WP9: Updates on dissemination activities (InfoTech)

Antonio (Infotech) updates the partners on dissemination activities (full presentation here). He informs the partners that by the end of the month Infotech will organize a virtual meeting with the Associate Partners and he invites all the dissemination managers to participate.

He shows the first results of the dissemination activities, already shared with the Dissemination Managers during an internal meeting.

At the end of the presentation, partners validate the brochure prepared by Infotech.

The meeting ends with Fedele final remarks. He informed that the EACEA has invited all Erasmus+ KA projects coordinators to interact on a Teams group where it is possible to share news and info about the projects. This will be a way also to share the questionnaires for the different surveys and enlarge the network. Moreover, Fedele reminds that the first project meeting (M6), that should have been taken place in Barcelona in April 2021, will be replaced by virtual sessions. ValueDo will prepare a doodle to set the most suitable days.